## Revised Product Backlog
Product Backlog
ID | User Stories | FEATURE | ESTIMATION
1 | As a passionate reader, I want to input my likes and dislikes into the system, so that the recommendation system can take them into account | Recommendation System | 2
2 | As a passionate reader, I want the system to generate recommendations based on my likes and dislikes so that I can get better recommendations. | Recommendation System | 8
3 | As a passionate reader, I want to view the recommendations generated based on my likes and dislikes and explore the books from the list. | Recommendation System | 2
4 | As a passionate reader, I want the system to generate recommendations that promote diversity and highlight authors from different backgrounds | Recommendation System | 8
5 | As a passionate reader, I want to be able to adjust my likes and dislikes so that I can refine the recommendations. | Recommendation System | 3
6 | As a new reader with no reading history, I want to receive basic recommendations based on popular and new authors, so that I can read more. | Recommendation System | 3
7 | As a new reader with no reading history, I want to specify my preferred genre so that recommendations are more tailored to my interests. | Recommendation System | 5
8 | As a new reader with no reading history, I want to explore recommended books with brief descriptions or summaries to help me decide, so I can read more. | Recommendation System | 3
9 | As a passionate reader, I want to be able to create a new list that I can name so I can organize and track my reading habits. | Book Collections | 2
10 | As a passionate reader, I want to add books to a specific list, such as liked/disliked or recommendations, so that I can keep track of books I have read or want to read. | Book Collections | 3
11 | As a passionate reader, I want to view and manage the books in my lists, including editing and deleting them, so that I can maintain an organized reading list. | Book Collections | 5
12 | As a passionate reader, I want my recommendations to be automatically added to a specific list for easy access, so that I can keep track of recommended books. | Book Collections | 3
13 | As a busy reader, I want to view detailed information about a book, including its description, author, and price, so that I can decide whether to purchase it. | Marketplace | 5
14 | As a busy reader, I want to add books to my shopping cart, so that I can purchase them later. | Marketplace | 3
15 | As a busy reader, I want to view and manage the items in my shopping cart, including adding, removing, and updating quantities, so that I can finalize my purchase. | Marketplace | 3
16 | As a busy reader, I want to have a smooth and secure checkout process, including entering my payment and shipping information, so that I can complete my purchase. | Marketplace | 5
17 | As a busy reader, I want to view my order history, including past purchases and order status, so that I can track my purchases. | Marketplace | 8
18 | As a busy reader, I want the option to use different payment methods when purchasing books, so that I am not limited to only one. | Marketplace | 3
19 | As a passionate reader, I want to be able to register for an account with my email address and password, so that I can access the application. | Login/Registration | 5
20 | As a passionate reader, I want to be able to register for an account with third party providers (Facebook, Google, etc), so that I can access the application and not have to remember another password. | Login/Registration | 3
21 | As a busy reader, I want to be able to reset my password if I forget it, so that I can regain access to my account. | Login/Registration | 2
22 | As a busy reader, I want to be able to log out, so I can end my session securely. | Login/Registration | 2